## Executive Summary
BookingOS AI Hub — QA Audit Report
Audit Date: April 03, 2026 ¦ Auditor: Head of QA ¦ Scope: AI Hub (Agents, Automations, Action Cards, Messaging Pipeline)
OVERALL ASSESSMENT
Metric | Value | Status
Total Bugs Found | 24 | NEEDS ACTION
Critical Severity | 7 | IMMEDIATE FIX
High Severity | 9 | SPRINT PRIORITY
Medium Severity | 5 | SCHEDULED
Low Severity | 3 | BACKLOG
Agents Tested | 5 of 5 | COMPLETE
Automation Triggers Tested | 6 of 9 implemented | GAP FOUND
Automation Actions Tested | 5 of 10 implemented | GAP FOUND
Existing Unit Tests (Pass) | 113 of 114 | 1 FAILURE
Test Suites with Parse Errors | 6 (.ts files) | ENV ISSUE
Integration Tests Exist | 0 | MISSING
Race Conditions Found | 5 | CRITICAL
Missing Trigger Implementations | 3 (MESSAGE_RECEIVED, CUSTOMER_CREATED, PAYMENT_RECEIVED) | GAP
Missing Action Implementations | 3 (SEND_TEMPLATE, ASSIGN_STAFF, SEND_NOTIFICATION) | GAP

## Agent Bugs
ID | Agent | Severity | Category | Bug Description | Impact | Recommended Fix | File / Line
AG-01 | WaitlistAgent | CRITICAL | Race Condition | Deduplication query and ActionCard creation are not atomic. Between checking for existing PENDING card and creating a new one, another thread can create a duplicate. | Duplicate cards sent to staff, customer contacted twice for same slot | Use Prisma transaction with serializable isolation or database-level UNIQUE constraint on (businessId, type, metadata.waitlistEntryId) | waitlist-agent.service.ts:93-133
AG-02 | WaitlistAgent | MEDIUM | Timezone | Date formatting uses toISOString().split('T')[0] which returns UTC date. For businesses in non-UTC timezones, this causes off-by-one date matching. | Slots matched for wrong day in non-UTC timezones | Use business timezone (Luxon/date-fns-tz) to format date strings | waitlist-agent.service.ts:~line 195
AG-03 | WaitlistAgent | LOW | Message Template | SMS template uses ${entry.customer.name} without null check. Empty name produces 'Great news ! A...' with double space. | Minor UX issue in customer-facing messages | Add fallback: customer.name ¦¦ 'there' | waitlist-agent.service.ts:~line 123
AG-04 | WaitlistAgent | MEDIUM | Validation | No validation that timeWindowStart/timeWindowEnd are valid HH:mm format, dateFrom <= dateTo, or durationMins > 0 | Silent failures matching invalid waitlist entries | Add input validation in validateConfig() or before processing | waitlist-agent.service.ts:~line 196-210
AG-05 | RetentionAgent | CRITICAL | Race Condition | Same deduplication race as WaitlistAgent — check-then-create is not atomic | Duplicate retention outreach to same customer | Use atomic upsert or transaction | retention-agent.service.ts dedup section
AG-06 | RetentionAgent | HIGH | Logic Error | Deduplication only checks for PENDING cards, not APPROVED or recently-created ones. If card is approved quickly, re-trigger creates another. | Customer gets multiple follow-ups from same retention trigger | Check for PENDING OR APPROVED cards created within last N days | retention-agent.service.ts dedup query
AG-07 | RetentionAgent | MEDIUM | Channel Detection | Channel detection falls back to WHATSAPP even if customer only has email. Social prefix exclusion (fb:, ig:) may miss new channel prefixes. | Message sent to wrong channel or fails silently | Use CustomerIdentityService for canonical channel resolution | retention-agent.service.ts channel logic
AG-08 | DataHygieneAgent | HIGH | Performance | O(n²) pair comparison for all customers in batch. With batchSize=100, this is 4,950 comparisons. For businesses with 10k customers, even batched this is very slow. | Agent timeout or excessive CPU during runs | Use database-level dedup (GROUP BY phone/email) to pre-filter candidates before pair comparison | data-hygiene-agent.service.ts comparison loop
AG-09 | DataHygieneAgent | MEDIUM | Logic Error | Levenshtein name matching uses 0.8 threshold but doesn't account for very short names. 'Bo' vs 'Bo' = 1.0 (match), 'Bo' vs 'Bob' = 0.67 (no match) — short names more sensitive to single-char differences. | Short customer names rarely match on name field even when they should | Use minimum name length threshold (e.g., skip Levenshtein for names < 4 chars) | data-hygiene-agent.service.ts Levenshtein section
AG-10 | SchedulingOptimizerAgent | HIGH | Logic Error | Uses toISOString() for date comparison same as WaitlistAgent. Also, gap detection only checks against PENDING/CONFIRMED/IN_PROGRESS bookings — doesn't account for blocked time, lunch breaks, or business hours. | False gaps detected during non-working hours or break times | Cross-reference with workingHours and blocked times before declaring a gap | scheduling-optimizer-agent.service.ts gap detection
AG-11 | SchedulingOptimizerAgent | LOW | Config | Agent is disabled by default in seed data for Glow Clinic and not configured for Metro Auto. No documentation on when/why to enable it. | Feature exists but is never exercised in demo/testing | Enable in seed data with conservative config, add documentation | seed-agentic.ts
AG-12 | QuoteFollowupAgent | HIGH | Logic Error | Priority formula uses totalAmount/100 assuming cents-to-dollars conversion. If business stores amounts in dollars (not cents), priority is artificially low. | Low-value quotes appear as lower priority than intended; high-value quotes capped early | Check business currency settings or normalize at query time | quote-followup-agent.service.ts priority calc
AG-13 | All Agents | CRITICAL | Concurrency | AgentFrameworkService.triggerAgent() has no distributed lock. If multiple API instances run the same agent simultaneously via cron, duplicate processing occurs. | All agents process same data twice, creating duplicate ActionCards across instances | Use Redis SETNX distributed lock with TTL before agent execution | agent-framework.service.ts triggerAgent()
AG-14 | All Agents | HIGH | Error Handling | ActionCard creation failure inside try/catch logs error but doesn't create any fallback notification. If Prisma is down temporarily, entire agent run produces 0 cards with no alerting. | Silent agent failures with no visibility | Add Sentry alerting for card creation failures; create fallback AgentRun error record | All agent files catch blocks

## Automation Bugs
ID | Agent | Severity | Category | Bug Description | Impact | Recommended Fix | File / Line
AU-01 | Executor | CRITICAL | Race Condition | In-memory `processing` flag prevents concurrent cron runs on SAME instance only. Multiple API instances each have their own flag — all process simultaneously. | Duplicate automation actions sent. Customer receives 2-3x messages from same rule across instances. | Replace with Redis distributed lock (SETNX with 55s TTL) | automation-executor.service.ts:13,29
AU-02 | Executor | CRITICAL | Race Condition | Step advancement (PENDING→RUNNING→WAITING→COMPLETED) uses separate Prisma update() calls, not transactions. Crash between updates leaves step in RUNNING state, re-processed on next cron. | Duplicate step execution — customer gets same message twice after server restart | Wrap state transitions in Prisma.$transaction() | automation-executor.service.ts:334-404
AU-03 | Executor | HIGH | Filter Logic | matchesFilters() uses strict equality (context[key] !== value). No support for: partial matching, case-insensitive comparison, array membership, range checks, or nested field access. | Rules that should fire don't fire (false negatives) due to type mismatch or case difference | Implement proper filter operators (EQUALS, CONTAINS, IN, RANGE, GT, LT) with type coercion | automation-executor.service.ts:739-746
AU-04 | Executor | HIGH | Template Rendering | renderTemplate() regex {{(\w+)}} only supports flat variable names. Cannot render {{booking.service.name}} or {{customer.email}}. Missing vars replaced with empty string silently. | Customer receives messages with missing data or literal {{variable}} text if nested vars used in template | Support dot-notation access: split key by '.', traverse object; add logging for unresolved variables | automation-executor.service.ts:810-812
AU-05 | Executor | HIGH | Missing Implementation | 3 trigger types declared in Prisma schema but NOT implemented in processRule() switch: MESSAGE_RECEIVED, CUSTOMER_CREATED, PAYMENT_RECEIVED | Automation rules with these triggers are silently ignored — they exist in DB and UI but never fire | Implement missing trigger cases in processRule() switch statement | automation-executor.service.ts:87-278
AU-06 | Executor | HIGH | Missing Implementation | 3 action types declared in schema but NOT implemented in executeActions(): SEND_TEMPLATE (distinct from SEND_MESSAGE), ASSIGN_STAFF, SEND_NOTIFICATION | Rules configured with these actions log 'SENT' but perform no actual operation | Implement missing action handlers with appropriate service calls | automation-executor.service.ts:561-686
AU-07 | Executor | MEDIUM | Step Workflow | DELAY step sets scheduledAt correctly but always advances to the NEXT step in sequence. If DELAY is the last step, stepId is set to current step.id (line 365: nextStep?.id ¦¦ step.id), causing infinite re-processing. | Last-step DELAY creates infinite WAITING→PENDING→WAITING loop consuming cron cycles | If no nextStep after DELAY, mark execution as COMPLETED immediately | automation-executor.service.ts:356-367
AU-08 | Executor | MEDIUM | Frequency Cap | Per-rule and global caps use today.setHours(0,0,0,0) which uses LOCAL server timezone, not business timezone. Day boundary differs across timezones. | Customer in different timezone may exceed or undercount daily limit | Use business timezone for day boundary calculation | automation-executor.service.ts:511-512,537-538
AU-09 | Executor | LOW | Pagination | Offset-based pagination (skip/take) with orderBy id:asc. If rules are deleted during iteration, skip offset shifts and some rules are missed. | Under rare conditions a rule is skipped for one cron cycle | Use cursor-based pagination (where: {id: {gt: lastId}}) | automation-executor.service.ts:36-62
AU-10 | Executor | CRITICAL | Step Execution | executeStepAction() only handles UPDATE_STATUS and ADD_TAG for step-based workflows. SEND_MESSAGE, SEND_EMAIL, WEBHOOK, and other actions are NOT implemented in step execution — only logged as 'SENT'. | Step workflows claim success but never actually send messages or trigger webhooks. Activity log shows 'SENT' for phantom actions. | Port action execution logic from executeActions() into executeStepAction() or create shared handler | automation-executor.service.ts:407-444

## Feature Gaps
ID | Area | Gap Description | Expected Behavior | Current Behavior | Impact | Priority
GAP-01 | Automation Triggers | MESSAGE_RECEIVED trigger not implemented in executor cron | Rules with MESSAGE_RECEIVED should fire when customer sends a message | Rules exist in DB/UI but processRule() has no case for it | Silently ignored | HIGH
GAP-02 | Automation Triggers | CUSTOMER_CREATED trigger not implemented | Rules should fire when a new customer is created | Same as GAP-01 — no case in switch | HIGH
GAP-03 | Automation Triggers | PAYMENT_RECEIVED trigger not implemented | Rules should fire on payment receipt | Same as GAP-01 | MEDIUM
GAP-04 | Automation Triggers | TESTIMONIAL_SUBMITTED trigger not implemented | Rules should fire when testimonial is submitted | Declared in enum but no handler | LOW
GAP-05 | Automation Triggers | CAMPAIGN_SENT trigger not implemented | Rules should fire when campaign completes sending | Declared in enum but no handler | LOW
GAP-06 | Automation Actions | SEND_TEMPLATE not implemented in executeActions() | Should look up message template by ID and render with variables | No handler — falls through; if action has no matching if-block, only logAction is called | HIGH
GAP-07 | Automation Actions | ASSIGN_STAFF not implemented | Should assign specified staff to booking/conversation | No handler | MEDIUM
GAP-08 | Automation Actions | SEND_NOTIFICATION not implemented | Should push notification to staff via FCM/Socket.IO | No handler | MEDIUM
GAP-09 | Step Workflow | executeStepAction() only handles UPDATE_STATUS and ADD_TAG | All action types should work in step-based workflows same as legacy executeActions() | SEND_MESSAGE, SEND_EMAIL, WEBHOOK, REQUEST_TESTIMONIAL all log 'SENT' but do nothing in steps | CRITICAL
GAP-10 | Agent Testing | Zero agent-specific unit/integration tests exist | Each agent should have dedicated test coverage for: execution logic, dedup, card creation, edge cases | Only framework-level tests exist (agent-framework.service.spec.ts, agent-scheduler.service.spec.ts) | HIGH
GAP-11 | Automation Analytics | Per-action outcome tracking missing | If a rule has 3 actions and 1 fails, the per-action breakdown should be visible | Only overall rule outcome logged; individual action failures hidden inside for-loop | MEDIUM
GAP-12 | ActionCard Executor | No CTA for 'merge' (DataHygiene) or 'check_waitlist' (SchedulingOptimizer) | These CTAs are defined in agent card metadata but executeCta() has no handlers for them | Unknown CTA returns error: {success: false, error: 'Unknown action'} | MEDIUM
GAP-13 | Email Templates | Email body in suggested messages uses \n\n for paragraphs | Should use proper HTML formatting for email clients | Plain text newlines may not render in HTML email clients | LOW
GAP-14 | Automation History | No CSV export of agent run history | Agent runs should be exportable like automation logs are | Automation logs have exportActivityLog() but agent runs have no equivalent | LOW

## Test Coverage
Component | Unit Tests | Integration Tests | Tests Pass | Edge Cases | Dedup Tested | Msg Templates Tested | Overall Grade
WaitlistAgent | NONE | NONE | N/A | NO | NO | NO | F
RetentionAgent | NONE | NONE | N/A | NO | NO | NO | F
DataHygieneAgent | NONE | NONE | N/A | NO | NO | NO | F
SchedulingOptimizerAgent | NONE | NONE | N/A | NO | NO | NO | F
QuoteFollowupAgent | NONE | NONE | N/A | NO | NO | NO | F
AgentFrameworkService | YES (spec exists) | NONE | PARSE ERROR | PARTIAL | N/A | N/A | D
AgentSchedulerService | YES (spec exists) | NONE | PARSE ERROR | PARTIAL | N/A | N/A | D
ActionCardService | YES (35 tests) | NONE | 35/35 PASS | YES | N/A | N/A | B
ActionCardController | YES (12 tests) | NONE | 12/12 PASS | PARTIAL | N/A | N/A | B
ActionCardExecutorService | NONE | NONE | N/A | NO | N/A | NO | F
AutomationService | YES (spec exists) | NONE | PARSE ERROR | PARTIAL | N/A | PARTIAL | D
AutomationExecutorService | YES (23 tests) | NONE | 22/23 PASS | YES | N/A | NO | B-
AutomationSteps | YES (13 tests) | NONE | 13/13 PASS | YES | N/A | N/A | A-
IntentDetector | YES (6 tests) | NONE | 6/6 PASS | PARTIAL | N/A | N/A | B
BookingAssistant | YES (state machine) | NONE | PASS | YES | N/A | N/A | A-
CancelAssistant | YES (state machine) | NONE | PASS | YES | N/A | N/A | A-
RescheduleAssistant | YES (state machine) | NONE | PASS | YES | N/A | N/A | A-
AI Service (orchestrator) | YES (spec exists) | NONE | PARSE ERROR | PARTIAL | N/A | N/A | D

## Test Results
Test Suite | File | Tests | Pass | Fail | Status | Notes
Action Card Service | action-card.service.spec.js (dist) | 35 | 35 | 0 | PASS | All scenarios covered: create, approve, dismiss, snooze, execute, expire, summary
Action Card Controller | action-card.controller.spec.js (dist) | 12 | 12 | 0 | PASS | Endpoint guards, roles, and response shapes tested
Automation Executor | automation-executor.service.spec.js (dist) | 23 | 22 | 1 | 1 FAIL | FAIL: 'skips when already processing' — timeout/race condition in test itself
Automation Steps | automation-steps.spec.js (dist) | 13 | 13 | 0 | PASS | Branch operators, step ordering, NotFoundException cases
Intent Detector | intent-detector.spec.js (dist) | 6 | 6 | 0 | PASS | All 6 intent types classified correctly
Vertical Action Handler | vertical-action-handler.spec.js (dist) | 21 | 21 | 0 | PASS | Aesthetic + Dealership vertical cards, stalled deal detection
Conversation Action Handler | conversation-action-handler.spec.js (dist) | 22 | 22 | 0 | PASS | Booking/Cancel/Reschedule confirm cards, low confidence, urgency
Agent Framework Service | agent-framework.service.spec.ts | 0 | 0 | 0 | PARSE ERROR | Babel cannot parse due to Prisma client platform mismatch (darwin→linux)
Agent Scheduler Service | agent-scheduler.service.spec.ts | 0 | 0 | 0 | PARSE ERROR | Same Prisma platform issue
Agent Controller | agent.controller.spec.ts | 0 | 0 | 0 | PARSE ERROR | Same Prisma platform issue
Automation Service | automation.service.spec.ts | 0 | 0 | 0 | PARSE ERROR | Same Prisma platform issue
AI Service | ai.service.spec.ts | 0 | 0 | 0 | PARSE ERROR | Same Prisma platform issue

## Fix Plan
Priority | Bug IDs | Fix Description | Effort (days) | Risk if Not Fixed | Suggested Sprint
P0 — Immediate | AU-01, AG-13 | Add Redis distributed lock for automation cron and agent triggers. Prevents duplicate processing across API instances. | 1 | Duplicate messages sent to customers on multi-instance deploys | Current Sprint
P0 — Immediate | AU-02 | Wrap step state transitions in Prisma.$transaction() to prevent duplicate execution on crash recovery. | 0.5 | Double message sends after server restarts | Current Sprint
P0 — Immediate | AU-10, GAP-09 | Port SEND_MESSAGE, SEND_EMAIL, WEBHOOK, REQUEST_TESTIMONIAL from executeActions() into executeStepAction() so step workflows actually send messages. | 1 | ALL step-based automations claim success but perform no real actions | Current Sprint
P1 — This Sprint | AU-05, GAP-01-05 | Implement missing trigger handlers: MESSAGE_RECEIVED, CUSTOMER_CREATED, PAYMENT_RECEIVED (+ TESTIMONIAL_SUBMITTED, CAMPAIGN_SENT) | 2 | 5 automation trigger types silently ignored | Current Sprint
P1 — This Sprint | AU-06, GAP-06-08 | Implement missing action handlers: SEND_TEMPLATE, ASSIGN_STAFF, SEND_NOTIFICATION | 1.5 | 3 action types log success but do nothing | Current Sprint
P1 — This Sprint | AG-01, AG-05 | Make agent deduplication atomic using Prisma transaction or DB constraint | 1 | Duplicate ActionCards created under concurrency | Current Sprint
P1 — This Sprint | AU-03 | Enhance matchesFilters() to support operators (EQUALS, CONTAINS, IN, RANGE), case-insensitive comparison, and type coercion | 1 | Rules with complex filters silently fail to match | Current Sprint
P2 — Next Sprint | AU-04 | Extend renderTemplate() to support dot-notation variables (booking.service.name) and log unresolved variables | 0.5 | Message templates with nested vars show empty content | Next Sprint
P2 — Next Sprint | AG-08 | Optimize DataHygieneAgent from O(n²) to pre-filtered candidates using SQL GROUP BY on phone/email | 1 | Slow agent runs or timeouts for businesses with many customers | Next Sprint
P2 — Next Sprint | AG-10, AG-12 | Fix SchedulingOptimizer gap detection to exclude non-work hours; fix QuoteFollowup currency assumption | 1 | False positive gaps; incorrect quote priority scoring | Next Sprint
P2 — Next Sprint | AU-07 | Fix DELAY as last step: if no next step, mark COMPLETED instead of re-pointing stepId to self | 0.5 | Infinite WAITING loop for automations ending with delay | Next Sprint
P2 — Next Sprint | GAP-10 | Write unit tests for all 5 agents: dedup, card creation, edge cases, message templates | 3 | No regression protection for agent logic changes | Next Sprint
P3 — Backlog | AU-08 | Use business timezone for frequency cap day boundary calculation | 0.5 | Minor over/under-counting at day boundary for non-UTC businesses | Backlog
P3 — Backlog | AU-09 | Switch to cursor-based pagination for automation cron | 0.5 | Very rare edge case where rules are skipped | Backlog
P3 — Backlog | GAP-12 | Add CTA handlers for 'merge' and 'check_waitlist' actions in ActionCardExecutorService | 1 | Staff sees CTAs that return errors when clicked | Backlog